## Cost Estimate
Zena J.Zahran
PAP I- Online
Section 01
| Time Estimate (hrs) | Actual Time Spent (hrs) | Difference | Rate
Week 1 |  |  |  | 45
A Course for Confidence | 2 | 1.5 | 0.5
Anchor Points | 2 | 0.75 | 1.25
Development | 2.5 | 8 | -5.5
Call to Action - Success! | 3 | 7 | -4
Project & Portfolio | 4 | 2 | 2
The Burn Up List | 2 | 0.5 | 1.5
Hours | 15.5 | 19.75 | -4.25
Week 1 - Profit/ Loss | 697.5 | 888.75 | -191.25
Week 2
Call to Action - Failure to Success! | 3 | 2.5 | 0.5
Mission Statement | 3 | 2.5 | 0.5
Project & Portfolio | 4 | 2 | 2
The Burn Up List | 2 | 3 | -1
Hours | 12 | 10 | 2
Week 2 - Profit/ Loss | 540 | 450 | 90
Week 3
Call to Action - Encouragement! | 3 | 3 | 0
Communicating with Visual Tools | 3 | 3 | 0
Project & Portfolio | 4 | 2.5 | 1.5
The Burn Up List | 2 | 3 | -1
Hours | 12 | 11.5 | 0.5
Week 3 - Profit/ Loss | 540 | 517.5 | 22.5
Week 4
Call to Action - Growth! | 3 | 4 | -1
SWOT/ SWOT Follow-up | 1.5 | 0.75 | 0.75
Being Paid for Your Work | 6 | 6 | 0
Time Estimation & Management | 16 | 12 | 4
Hours | 26.5 | 22.75 | 3.75
Week 4 - Profit/ Loss | 1192.5 | 1023.75 | 168.75
Estimate/ Actual Monthly cost | 2970 | 2880 | 90
Loss
Profit

## Estimate with Dynamic Formula
Zena J.Zahran
PAP I- Online
Section 01
| Time Estimate (hrs) | Actual Time Spent (hrs) | Difference | Rate
Week 1 |  |  |  | 45
A Course for Confidence | 2 | 1.5 | 0.5
Anchor Points | 2 | 0.75 | 1.25
Development | 2.5 | 8 | -5.5
Call to Action - Success! | 3 | 7 | -4
Project & Portfolio | 4 | 2 | 2
The Burn Up List | 2 | 0.5 | 1.5
Hours | 15.5 | 19.75 | -4.25
Week 1 - Profit/ Loss | 697.5 | 888.75 | -191.25
Week 2
Call to Action - Failure to Success! | 3 | 2.5 | 0.5
Mission Statement | 3 | 2.5 | 0.5
Project & Portfolio | 4 | 2 | 2
The Burn Up List | 2 | 3 | -1
Hours | 12 | 10 | 2
Week 2 - Profit/ Loss | 540 | 450 | 90
Week 3
Call to Action - Encouragement! | 3 | 3 | 0
Communicating with Visual Tools | 3 | 3 | 0
Project & Portfolio | 4 | 2.5 | 1.5
The Burn Up List | 2 | 3 | -1
Hours | 12 | 11.5 | 0.5
Week 3- Profit/ Loss | 540 | 517.5 | 22.5
Week 4
Call to Action - Growth! | 3 | 4 | -1
SWOT/ SWOT Follow-up | 1.5 | 0.75 | 0.75
Being Paid for Your Work | 6 | 6 | 0
Time Estimation & Management | 16 | 12 | 4
Hours | 26.5 | 22.75 | 3.75
Week 4 - Profit/ Loss | 1192.5 | 1023.75 | 168.75
Estimate/ Actual Monthly cost | 2970 | 2880 | 90
Loss
Profit